## Slide 1: STREAM – WP6 – Impact, dissemination & capitalisation
WP6 lead - City of Dublin ETB, co-lead Metropolis

## Slide 2: Work Package 6 - Objectives
Development and mainstreaming of recommendations to policy makers on use and validation of micro-credentials. This includes raising awareness on the benefits and exploitation opportunities of micro-credentials.
Strengthening VET organisations capacity to build and manage micro-credentials and building a common understanding of micro-credential methodology.

## Slide 3: Work Package 6 - Objectives
Engaging target groups and stakeholders in the activities of the STREAM project (field research, pilots, workshops, exploitation) to build awareness and knowledge.
Building a task of Ambassadors to spread the European Professional Certificate for practitioners in Inclusive, Digital and Green Work-Based Learning.
Widespread the activities and the visibility of Micro-credentials for VET by promoting the use of STREAM’s results by different stakeholders during and after the implementation of the project.

## Slide 4: Target Groups
European VET community of VET practitioners - VET programme organisers and course designers; VET tutors, trainers and teachers; industry liaison staff;
Company representatives (work-based learning; human resources) working with VET institutions on recruitment, retention and industry trends; those with responsibility for quality assurance in VET; trade association experts, skills forecasting managers responsible for building organizational capability and professional development of their staff) ;
Stakeholders involved with employment labour market - institutes, centres for research in entrepreneurship, small firms and corporate studies and professional development, including applied research; but also economists, social psychologists with an interest in workplaces and those with an interest in inclusive education.

## Slide 5: T6.1 - Website
A well-structured, informative and up-to-date website.
  Provide a description of the project and its aims and future goals.
  Provide a description of each partner with contacts and links to their websites.
  A page that will contain all the product and resources of the project related to the WPs.
  A page with news about the state of the project.
Updated regularly to ensure visibility of progress of the project.

## Slide 6: T6.2 – Social Media Platforms
Development of a dissemination and exploitation strategy to include:
  Infographics
  Timeline of dissemination activities.
  Dissemination responsibilities per partner.
  Stakeholder engagement plan.
  Social media strategy – 10,000+ target reach.
  Dissemination strategy for recruitment of participants for pilots
A visual brand identity – logo, templates etc.

## Slide 7: T6.3 – Tutorial for micro-credentials framework (D6.1)
Interactive tutorial on how to build and implement a micro-credentials (MC) framework.
To raise awareness of the possibility to:
  Join the STREAM framework.
  And/or build a new MC framework.

## Slide 8: T6.4 – Paper on micro-credentials validation (MS13/D6.2)
Paper on micro-credentials validation – recommendations for policy makers
  How to implement micro-credentials.
  How to connect them with the national qualification framework in partner countries.
  Expert group session – September 2025 (M9) – Madrid TPM to identify the basis for this report.

## Slide 9: T6.5 – STREAM Ambassador Award
Digital open badge ‘STREAM Ambassador’ – for disseminating project’s outcomes
Actively engaging in exploitation actions and in promoting the use of STREAM across:
  Communities of Practices in EPALE.
  Virtual CoPs of VET practitioners managed by MetropolisNet & other partners.

## Slide 10: T6.6 – Final Conference (MS14)
One day international event November 2026 (M35) – adjacent to Berlin TPM
At least 100 participants and key policy-makers (1-2 per country)
Two round tables – HE & VET – future transitions & pathways.
Promotional material to include:
  Website announcement, social media posts.
  Agenda, email campaign with all material provided in English.

## Slide 11: Milestones & Deliverables
MS13/D6.2 – Paper on micro-credentials validation – initiated in M9 (workshop in Madrid) – delivered M25 (January 2026) – MetropolisNet
MS14 – Final conference - MetropolisNet
D6.1 – Tutorial to build and implement a MC framework – initiated M26 (February 2026) – delivered M35 (November 2026) – City of Dublin ETB

## Slide 12: Conclusions
Dissemination – integral part of project life cycle.
Runs parallel to the working program and adjusts to match the main activities at each phase.
All suggestions for changes or enhancements that support the promotion of the project will be welcomed by the leading partners.

## Slide 13
City of Dublin ETB & MetropolisNet
This Photo by Unknown Author is licensed under CC BY