## Slide 1: STREAM Blueprint for inclusive, digital and green Work Based Learning (WBL)
WP4 IDEC, co-lead by CIOFS FP ETS
Month 12 to 34

## Slide 2: WP4: STREAM in practice (piloting and assessment)
Objectives
Identification of the target and recruitment
Definition of the Pilot Implementation Plan
Equip VET trainers and Companies’ mentors with the competences to plan and manage Inclusive, digital and Green WBL, in their countries and abroad
Test the newly acquired competencies during the WBL planning and management
Recollection of RPL
Assessment of the piloting

## Slide 3: T4.1 CoP recruitement (led by IDEC)
The recruitment, selection and engagement of the 10 VET trainers and companies’ mentors in 5 countries (50 across IT, EL, SP, IE and LT) that will be involved in the piloting starting in M14.
The recruitment, face -to face and on line, will be informed by the list of Prerequisites identified in WP3 – STREAM Micro-credentials design.
One partner per country will be in charge to finalize the Learning agreement with the selected participants and manage the Pilot Implementation

## Slide 4: T4.2 Definition of the pilot implementation plans (IDEC)
The WP Leader, will be responsible for defining the concrete steps to implement the 3 components of the pilot in each partner country. (See Section 2.1.1 per further details on the contents).
The implementation plan will include details on the timing and procedures for implementing the pilot, also according to the specificities of each local context.

## Slide 5: T3.3 Piloting component I - Competence Assessment and prior learning recognition (CIOFS-FP)
The delivery of training is underpinned by the personalization of individual learning paths, in order to maximise impact and the use of resources. To this end, the 50 trainers identified when recruiting will undergo an assessment of their previously acquired skills, with reference to the WP3. Stream micro-credential system.
In addition, the initial skills assessment, coupled with a final assessment will help trace the learning journey followed by each learner

## Slide 6: T4.4 Piloting Component II – Piloting the LMS with trainers and MC delivery, including digital badges
The 50 trainers identified will be involved in the STREAM online training on the 3 STREAM Modules.
The contents selected, reviewed and adapted on WP3 will be progressed in this part of the pilot.
The structure of the intervention – lasting 4 months, from M15 to M19 will be:
1. Introduction session led by the responsible partner organization in each country
2. Participants working through the selected Micro-Credentials on their own in the digital environment;
3. Scheduling and taking part in 2 online transnational/national exchange seminar sessions, within the Community of Practice to help successfully complete the modules.

## Slide 7: T4.5 Piloting Component III – Testing the acquired competences with students and apprentices (IDEC)
The third phase of the piloting involves testing STREAM skills in the practice of designing and managing WBL experiences, in their own country and in mobility.
To this end, two WBLs per country will be tested. In each one of them, the impact of the training on the students themselves will also be analysed, through a rigorous evaluation that is part of the Impact assessment.
This pilot will follow a lean approach that will allow to check and eventually adjust the process. To this aim, two workshops with partners and practitioners will be organized at M20 and M25

## Slide 8: T4.6 Piloting evaluation (CIOFS-FP ETS)
An external evaluator will be specifically in charge to assess the processes, the achievements and results within the pilots both in terms of
1. Strengthening capacities of VET/ companies’ staff involved in WBL and mobilities according to the STREAM professional profile;
2. Highlights, challenges and bottlenecks encountered in the implementation;
3. Recommendations and lessons learnt in relation to the STREAM MC framework development, sustainability and transferability.

## Slide 9: T4.7 STREAM accreditation phase 2
Following the results of the pilot, FU and FHM will revise the accreditation performed under WP2 and consolidate it in the light of the concrete experiences undertaken.

## Slide 10: Events - Milestones
M19 online
Workshop "Train the Trainers"
M25 Athens
Workshop "Train the practice"

## Slide 11: Deliverables
D4.1 Pilot evaluation plan & report M35

## Slide 12: Thank you for your attention! Natassa Kazantzidou, IDEC natassa@idec.gr